# Action Plan 2016-2019

# The following strategic action plan outlines the goals and objectives for the association.

FUNDING

| PURPOSE: Increase funding for LHDs & AOHC. |
| --- |
| Goal 1: Increase funding for LHDs & AOHC | Strategies | Responsible Party | Potential Partners | Target Date | Status |
| 1.) Increase subsidy funding for LHD’s by at least $2.00 per capita, to pay for unfunded mandated programs by 2019. | Engage legislators at State office and Director of Health | -AOHC Board -Public Health Future Committee | RWJF Universities OSU-PH Health Policy Inst. of Ohio | 12/31/2016 | Budget bill included increase for accredited LHDs to $.35 per capita |
|  | Link outcomes to funding support | (Lead TBD) |  |  |  |
|  | Document & quantify Public Health services on per capita baseline data |  |  | 12/31/2017 | 21C costing group ready to pilot FPHS costing tool |
|  | Return on investment | RWJF-Terry Allen | ODH CCBH |  |  |
| 2.) Ensure sustainable funding to support Accreditation efforts for LHD’s at a minimum $60,000. | Meet with ODH Director to establish a dedicated line item in the Ohio Budget | -AOHC Officers (Lead TBD) | ODH LHD’s | 12/31/2017 | Budget included funds for planning alignment, doubling of subsidy for accredited LHDs, support for merging LHDs. OSU project includes $1.89 million for accreditation assessment and support. |
|  | Finalize immediate funding for supporting LHD’s using ODH general revenue funds. | AOHC Lobbyist |  |  | See above |
|  | Increase Tobacco tax |  | American Cancer Society American Lung ODH |  | Budget included a modest increase in tobacco tax, no designation for Public Health |

| Goal 2. Increase AOHC overall support to LHD’s | Strategies | Responsible Party | Potential Partners | Target Date | Status |
| --- | --- | --- | --- | --- | --- |
| 3.) AOHC directly compete for federal funding (act as fiscal agent). | Become 501C3 or establish one. | AOHC | LHD’s Foundations Government Agencies | 12/2017 | Subcommittee met with accountant to discuss feasibility of different options. Expert opinion was to establish a separate 501(c)3. |
|  | Fiscal Agent |  |  |  |  |
|  | Grant writing capacity |  |  |  |  |
|  | Grant identification |  |  |  |  |
| 4.) Restructure AOHC dues to assure financial stability into the future, given the loss of number of LHDs through merger, etc. | a. Establish plan to assure continued financial stability of AOHC. b. Pursue dues options that would increase advocacy capacity. | AOHC Finance Committee and board |  | Spring Conference 2018 Member approval Fall 2018 | To be discussed at next meeting: Examine current dues structure and business plan. Recommend revisions that account for mergers of smaller districts. Look at upper dues limit, especially. |

ADVOCACY

| PURPOSE: Advocate and support local public health in Ohio through AOHC |
| --- |
| GOAL #1: AOHC Policy Advocacy | Strategies | Responsible Party | Potential Partners | Target Date | Status |
| OBJECTIVES: Develop legislative/policy priorities for AOHC to address in the coming year | AOHC Public Health Platform (Spring Conference members review/feedback; Fall Conference final document) | AOHC Board and Exec. Director | AOHC Lobbyist AOHC Board AOHC membership | September 2017 | Platform is close to finalization, after expansion, inclusion of data. |
|  | AOHC Public Health Priorities | Jason Orcena |  | January 31, 2017 | Priorities document approved in March 2017. |
| Educate legislators on AOHC policy priorities and local public health. | 2a“Storm the legislature” April 25-26 2017 | Beth and Aaron create document, pick date, get AOHC members with a goal of as many members and health commissioners as needed. | AOHC Board, AOHC staff, AOHC Lobbyist, Legislative Aides | April 25-26 2017 | Scheduling precluded event in 2017; working toward Vaccinate and Educate event in Fall 2018. |
|  | Health District outreach by health district. Protocol adding the legislature to press releases locally (Immunization rates, accreditation) Template and quarterly by region. AOHC push out to members > members to push out to legislators. Consider better using the newsletters. | AOHC Exec. Director, staff, Lobbyist, and AOHC members | AOHC Public Affairs Committee & Board, Legislative aides | Set up quarterly – begin in 2017 & ongoing |  |
| Ensure that all AOHC members are aware of the policy priorities for the current year | AOHC – update on NACCHO information to the Ohio Senators. | AOHC Exec. Director, staff and Lobbyist | AOHC Public Affairs Committee & Board, Legislative aides | Set up quarterly – begin in 2017 & ongoing |  |
|  | Develop a Legislature contact guide for AOHC members | AOHC Exec. Director, staff and Lobbyist | AOHC Public Affairs Committee & Board, Legislative aides | February 28, 2017 with routine revisions | Currently using online look-up feature |
|  | Ensure that all AOHC members are aware of the policy priorities for the current year. Talking points for the members to talk with legislators (Aaron’s PowerPoint from Health Commissioner’s University) to a one pagers | AOHC Public Affairs Committee & Board, Exec. Director | AOHC Lobbyist | April 20, 2017, with routine revisions |  |

WORKFORCE DEVELOPMENT

| PURPOSE: Offer training opportunities for all levels of employment at local health districts. |
| --- |
| STRATEGIC PRIORITIES Goals & Objectives | Strategies | Responsible Party | Potential Partners | Target Date | Status |
| The AOHC will develop and implement a training needs survey for LHDs, and develop an annual training plan by September 30, 2017. | Identify current sources of training needs for LHD based or individual WFD plans | AOHC Workforce Development Committee | OSU CPH, WSU | March 31, 2017 | Current evaluation responses used by Fall Conference Planning Committee in March – May 2017 to plan conference. |
|  | Analyze those results to determine if overall survey is needed i. Develop and administer survey if needed. Analyze survey results. |  |  | April 30, 2017 June 30, 2017 July 31, 2017 |  |
|  | Develop plan that includes topics, resources, various means of delivery and responsible party for each |  |  | August 30, 2017 | The subcommittee wanted to complete assessment and integration of existing options prior to considering an overall plan. |
|  | Submit plan to AOHC board for approval. |  |  | September 30, 2017 |  |
| The AOHC will develop a curriculum for each of the identified needs as prioritized by the AOHC Board by December 31, 2017. | Review evidenced best/past practices training needs area. Determine subject matter expert. Identify method and responsible party for curriculum development. Develop consistent evaluation tool for all AOHC offering. Implement training and include an evaluation for ongoing program improvement (AOHC approved tool) | AOHC Workforce Development Committee & AOHC Board | OEHA, OPHA, SOPHE, OSU, WSU, HPIO, Columbus State | December 31, 2017 | Leads of each offering are working together to compare content, integrate the offerings into a progressive approach. |
| The AOHC will continue with current trainings, to include: HCU, NET, Skillsoft, Legendary Service, and LEHDS with a minimum of one training per year on-going through 2021. | AOHC will review update the annual training plan to ensure that a continuous training schedule is mapped out through the year 2021 or beyond. Flexibility to add more training or address discrepancies will be included. The training subcommittee will review all attendee evaluations annually land make changes to curriculum to assure CQI. Annually all evaluations, curriculums, and recommended trainings will be presented to the AOHC board for approval. | WFD committee Training subcommittees | Columbus State | On-going through 2021 | Presentations in 2017: HCU with 2 in person sessions and 2 webinars; 2 LEHDS, 3 New Employee Training, 1 Legendary Service. Skillsoft contract renewed for second 3-year period, with the addition of IT option. |

SHARED SERVICES

| PURPOSE: Identify need and mechanisms of providing shared services for LHDs. |
| --- |
| Goal 1: Assess shared service needs of Local Public Health Departments. | Strategies | Responsible Party | Potential Partners | Target Date | Status |
| Objectives Conduct statewide assessment of perceived needs for sharing services. | Develop key informant study of program gaps in particular areas looking for commonalities. Human Resources PHAB Accounting Contracts/grants to provide services Information Technology services Purchased service savings. Etc. | AOHC Board and/or LPHSC Board | Colleges of Public Health in Ohio | 8-1-2016 | 21 C groups (shared services and small LHD) conducted survey; high level analysis of results completed. Groups are currently working with the Center for Shared Services at the University of Kansas to conduct a deeper analysis. |
| Develop process for ongoing identification of shared service needs as PH changes and evolves. |  | AOHC Board and/or LPHSC Board |  | ongoing |  |
| Study feasibility of AOHC hiring a “Business Development Executive” with purpose of leading and building “Shared Services” product lines. | Fund through pursuit of foundation grants and/or AOHC equity seed money. | AOHC Board and/or LPHSC Board |  | 10-1-2016 | Part-time Operations Coordinator for LPHSC approved for 2018. |

MEMBER ENGAGEMENT

| STRATEGIC PRIORITIES Goals & Objectives | Strategies | Responsible Party | Potential Partners | Target Date | Status |
| --- | --- | --- | --- | --- | --- |
| Member Engagement |  |  |  |  |  |
| Goal 1: Improve communication among membership |  |  |  |  |  |
| Objective 1.1 Gather information on communication needs by May 31, 2017 | Develop a subcommittee to work on a survey Conduct survey of membership on communication to determine need to expand modes of communication and member preferences Review survey results and make recommendations to the AOHC Board on ways to improve communication Incorporate approved recommended changes into AOHC procedures | AOHC Member Engagement Subcommittee | AOHC Director, AOHC Support Staff, AOHC Members | June 2016 March 2017 May 2017 December 2017 | Completed Completed Completed Completed |
| Objective 1.2 Increase transparency among membership by December 31, 2019 | Disseminate Key Points out to membership following Public Affairs and Board Meetings Semi-annually disseminate highlights on key accomplishments/ issues Include the strategic plan and annual updates on the members only section of the AOHC website, include accomplishments in annual highlights Provide direct links to minutes in the weekly newsletter Provide AOHC Public Affairs and Board minutes in draft form on the members only section of the website Develop a protocol on how and when member polling on key issues will be used | AOHC Member Engagement Subcommittee | AOHC Director, AOHC Support Staff, AOHC Members | Ongoing Ongoing Dec. 31, 2017 and ongoing July 1, 2017 July 1, 2017 July 31, 2017 | Many of these activities have been initiated and will be ongoing. |
| Objective 1.3 Develop Messaging Techniques to improve Consistency of Communication among employees and members by December 31, 2019 | Provide key talking points related to AOHC positions, white papers and key priorities and disseminate to all members | AOHC Board Members, Public Affairs Committee Members | AOHC Members, AOHC Director, AOHC Support Staff | Ongoing |  |
| Goal 2: Improve Marketing and Branding of AOHC as a strong state public health association |  |  |  |  |  |
| Objective 2.1 Promote Resources available to members through multiple marketing strategies and communication pathways by December 31, 2019. | Market association services to members and external stakeholders via emails, flyers, brochures, newsletters, testimonials, and announcements at spring and fall conferences | AOHC Director | LPHSC, Workforce Development Subcommittee | Ongoing |  |
| Objective 2.2 Promote Association accomplishments and successes through multiple communication pathways by December 31, 2019. | Highlight successes and accomplishments via: Newsletter Spring and fall conferences website | AOHC Director | AOHC Board Members | Ongoing |  |
| Goal 3: Engage Membership |  |  |  |  |  |
| Objective 1.1 Engage new health commissioners to participate in one or more: the AOHC Board, Public Affairs, District Meetings, or Subcommittees | Develop fact sheet for all new health commissioners to make them aware of critical tasks and deadlines Have existing Public Affairs members personally invite new health commissioners to attend the Public Affairs meeting | Workforce Development Subcommittee Public Affairs Members |  | December 31, 2017 Ongoing | New HC luncheon held at Fall Conference for the third year. |